## Sheet1
The testing of the mysangathi phase -II
sl no | Module | Bug Name | Bug Desc | Bug ID | Status | Priority | Resource | Logged date | UI Issuse | completed date | tested | tested date
1 | Registartion | The age is restracting for female is 18yrs | Go to the mysangathi->give the information->select the date of birth 18 yrs as the female->click on the registartion->the age is restrcting for 18yrs | RE-1 | Open | High | Vijay | 2013-04-04 | completed |  | javed | 19-04-13
2 | Registartion | The messege is not showing the proper for the male age restrcition | Go to the mysangathi->give the information->select the date of birth 18 yrs as the male->click on the registartion->the messege is not showing proper | RE-2 | Open | Medium | Vijay | 2013-04-04 | completed |  | javed | 19-04-13
3 | Registartion | The messege is not showing the proper for the female age restrcition | Go to the mysangathi->give the information->select the date of birth 18 yrs as the female->click on the registartion->the messege is not showing proper | RE-3 | Open | Medium | vijay | 2013-04-04 | completed |  | javed | 19-04-13
4 | Forget password | The page not shown | Go to mysangathi->click on the forget password->the page is not shown | FP-1 | Open | Show stopper | javed | 2013-04-04 | completed |  | javed | 19-04-13
5 | Caste | The castes mention in the registration in not mention in the search | Go to mysangathi->login to the account->select the caste in the search->the castes is not displaying as shown in the registration page | CS-1 | Open | Medium | javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
6 | Change password | The java null pointer exceptions | Go to the mysangathi->fill the information->click on the register->login to the mailid->click on the activation url->click on the save password | CP-1 | Open | Show stopper | Javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
7 | Search | The java null pointer exceptions | Go to mysangathi->login into the application->select the url click on the enter->the java null pointer excpections occurs | SE-1 | open | Show stopper | Javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
8 | Change password | The username can be editable | Go to the mysangathi->login into the account->click on the changepassword->the username can be editable | CP-1 | Open | High | javed | 2013-04-04 | completed | 19-04-13 | javed | 19-04-13
9 | Change password | Java null pointer exceptions | Go to the mysangathi->login into the account->click on the changepassword->give the new password->give the different conform password->and again give the proper password click on the change password->A null pointer exceptions occurs | CP-2 | Open | Show stopper | javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
10 | Change password | The application is logout | Go to the mysangathi->login into the account->click on the changepassword->click on the home->the application is logout | CP-3 | Open | High | javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
11 | Change password | The alert message is not showing | Go to the mysangathi->login into the account->click on the changepassword->give the password less than 6->click on thechange password->the alert messege is not proper | CP-4 | Open | High | javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
12 | Change password | The alert message is not showing | Go to the mysangathi->login into the account->click on the changepassword->give the password less than 6-> click on the change password->the alert is showing the conform is doesn’t match where conform password | CP-5 | Open | High | javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
13 | Changepassword | The password is not checking for the old password | Go to the mysangathi->login into the account->click on the changepassword->give the new password same as old password->click on the change password->the new password is taking the old password | CP-6 | Open | High | javed | 2013-04-04 | completed(**)
14 | Changepassword | the old password is not validating | Go to the mysangathi->login into the account->click on the changepassword->give the wrong old password->give the new password->click on the change password->the old password is not validating | CP-7 | Open | High | javed | 2013-04-04 | completed | 18-04-13 | javed | 19-04-13
15 | Changepassword | check the alert messege | Go to the mysangathi->login into the account->click on the changepassword->click on the change password without giving any information->the alert messege is not proper | CP-8 | Open | High | javed | 2013-04-04 | completed | 18-04-13 | javed | 20-04-13
16 | Changepassword | Java null pointer | Go to the mysangathi->login into the account->click on the changepassword->give the new password->give the conform password->click on the change password the null pointer exceptions occurs | CP-9 | Open | Show stopper | javed | 2013-04-08 | completed | 18-04-13 | javed | 20-04-13
17 | Changepassword | The password is taking less than 6 charcters | Go to the mysangathi->login into the account->click on the changepassword->give the current password->give the new password & conform password less than 6->click on the change password->the password is changing | CP-10 | Open | High | javed | 2013-04-08 | completed | 18-04-13 | javed | 20-04-13
18 | Changepassword | The null pointer exceptions | Go to the mysangathi->login into the account->click on the change password->give the different current password->without the username->give the new password&conform password->click on the change password ->the null pointer exceptions | CP-11 | Open | Show stopper | javed | 2013-04-08 | completed | 18-04-13 | javed | 20-04-13
19 | Changepassword | The password can change other username | Go to the mysangathi->login into the account->click on the change password->give the username of other->give the old password->give the new password->give the conform password->click on the change password->the password of other username can be changed | CP-12 | Open | High | javed | 2013-04-08 | completed | 18-04-13(**).
20 | Forgot password | HTTP Status 404 occurs | Go to the mysangathi->click on the forget password->give the emailid->click on the forget password->the http 404 error occurs | FP-01 | Open | Show stopper | javed | 2013-04-08 | completed | 19-04-13 | javed | 20-04-13
21 | Forgot password | Null pointer exceptions | Go to the mysangathi->click on the forget password->click on the forgot password without any information->a null pointer exceptions occurs | FP-02 | Open | Show stopper | Vijay | 2013-04-08 | completed | 19-04-13 | javed | 20-04-13
22 | Forgot password | Null pointer exceptions | Go to the mysangathi->click on the forget password->give the email id not email format->click on the forgot password->a java null pointer exceptions occurs | FP-03 | Open | Show stopper | javed | 2013-04-08 | completed | 19-04-13 | javed | 20-04-13
23 | Forgot password | There is no validation for email format | Go to the mysangathi->click on the forget password->give the email id not email format->click on the forgot password->there is no email validation | FP-04 | Open | High | Vijay | 2013-04-08 | completed | 19-04-13 | javed | 20-04-13
24 | Refrence id | The messages is not proper | Go to the mysangathi->login to the account check the message displaying refrence id in the search option | RI-01 | Open | High | javed | 2013-04-08 | completed | 19-04-13 | javed | 20-04-13
25 | Refrence id | The refrence id is not showing proper change in the database | Go to the mysangathi->change the refrence id from the database->click on the login providing username password->login to the application->check the rerence id | RI-02 | open | High | javed | 2013-04-08 | completed(**)
26 | Update profile | the path of the horscope is showing | Go to the mysangathi->login to the application->update the photo->click on the update->the the horscope path is displaying as selected | UP-01 | Open | High | Javed | 2013-04-08 | completed |  | javed | 20-04-13
27 | profession | The profession mention in the registration in not mention in the Update | Go to mysangathi->login to the account->select the profession in the search->the profession is not displaying as shown in the registration page | CS-2 | Open | Medium | javed | 2013-04-08 | completed |  | javed | 20-04-13
28 | Religion | The religion of the karnataka is not showing | Go to mysangathi->select the religion in the regisration-> there is no full religion of the karnataka | CS-3 | Open | Medium | javed | 2013-04-08 | completed |  | javed | 20-04-13
29 | Download horoscope | Showing the error called refrence id | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the download link-> The ReferenceID is required occurs | DH-01 | Open | High | Javed | 2013-04-08 | completed |  | javed | 20-04-13
30 | Download horoscope | The horoscope path is not showing | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the change horoscope->click on the update button->the horoscope path is storing old one | DH-02 | Open | High | Javed | 2013-04-08 | completed |  | javed | 20-04-13
31 | Download horoscope | The horscope can be download | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the change horoscope->the browse button->click on the document download->the old document will download | DH-03 | Open | High | Javed | , | completed |  | javed | 20-04-13
32 | Download horoscope | The download horscope will be the msword | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the browse button->browse the text file->click on the update->once again->give refrence id->click on the search->click on the download horoscope->the file always show in the ms word format | DH-04 | open | High | Javed | 2013-04-08 | completed |  | javed | 20-04-13
33 | Photo | The automatically the photo is taking path | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the browse button->browse the text file->click on the update->once again->give refrence id->click on the search->the photo path will be took automatically | PH-01 | Open | High | Javed | 2013-04-08 | completed |  | javed | 20-04-13
34 | Download horoscope | The old path is storing | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the browse button->click on the update->once again->give refrence id->click on the search->the old path of horoscope is shown | DH-05 | open | High | Javed | 2013-04-08 | completed |  | javed | 20-04-13
35 | Download horoscope | The path is not shown in the database but it is shown as a path | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the browse button->click on the update-> delete the path in the database->the path will be shown in the UI | DH-06 | Open | High | Javed | 2013-04-08 | completed |  | javed | 20-04-13
36 | Download Horoscope | The connection was reset | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the browse->select the file more 1mb->click on the update->the connection was reset error occurs | DH-07 | open | High | Javed | 2013-04-08 | completed | 20-04-13 | javed | 20-04-13
37 | Download Horoscope | Only ms word file open | Go to mysangathi->login as admin->give refrence id->click on the search button->click on the browse button->browse the text file->click on the update->once again->give refrence id->click on the search->click on the download horoscope->click on the open with->only ms word file can view not other files | DH-08 | Open | High | Javed | 2013-04-08 | 80% completed | ms-word file will give download option and pdf file directly opening. This is the problem
38 | Fargotpassword activation link validatition | for all the fields | toGo to the mysangathi->click on the forget password-> give the email id-> check the mail and the the validaton is not done proper | FP-09 | Open | High | Javed | 2013-04-08 | completed | 19-04-13 | javed | 20-04-13
39 | admin message action | in viewprofile | Go to mysangathi->login as admin-> search->interested profile the action message problem | vp-01 | open | High | javed | 2013-04-08 | 80%completed | proble is its working one interest but more than one interest its taking the list. This is the problem